## Cover
Amazon.com Website Test Plan
Portfolio-ready QA workbook ¦ Functional, non-functional, traceability, execution, bugs, and dashboard
| Prepared By | Alain Joseph A. Velasquez
| Document Version | 2.0
| Prepared Date | 2025-07-14
| System Under Test | Amazon.com (public e-commerce website)
| Purpose | Demonstrate structured QA planning, execution readiness, and reporting
Workbook Contents
| 1. Cover | Overview and submission-facing summary
| 2. Test Plan | Scope, objectives, environments, entry/exit criteria, deliverables
| 3. Scope & Risks | In scope / out of scope, assumptions, risks, mitigations
| 4. Scenarios | Scenario catalogue with module, type, priority, and automation fit
| 5. Test Cases | Detailed manual test cases with steps and expected results
| 6. RTM | Requirements traceability matrix
| 7. Execution Tracker | Execution planning and status tracking
| 8. Bug Tracker | Defect log with severity, priority, and aging
| 9. Dashboard | KPI summary and charts
Tip: Replace placeholder values in blue-shaded input cells before sending as part of an application.
Note on C8: Replace with your full name before submitting.

## Test Plan
Master Test Plan
Document Control
Item | Details | Owner | Notes
Project | Amazon.com website testing | QA
Prepared by | Your Name | QA
Version | 2.0 | QA
Review status | Draft / Ready for submission | QA
Objectives
Item | Details | Owner | Notes
Primary objective | Validate that Amazon.com supports reliable product discovery, cart, checkout, account, and post-purchase experiences. | QA
Quality goals | Accuracy, usability, responsiveness, compatibility, accessibility, and core-flow reliability. | QA
Test Scope
Item | Details | Owner | Notes
In scope | Home page, navigation, search, product detail page, cart, sign-in, checkout, order confirmation, order history, global UI, responsiveness, basic accessibility and security checks. | QA
Out of scope | Internal admin tools, fulfillment systems, seller portals, payment processor internals, and deep API-only validation. | QA
Approach
Item | Details | Owner | Notes
Functional testing | Risk-based manual testing focused on high-value customer flows and edge cases. | QA
Regression strategy | Smoke regression for core customer journey after each critical fix or release candidate. | QA
Automation strategy | Automate stable paths first: login, search, add to cart, cart updates, and checkout happy path. | QA
Environment
Item | Details | Owner | Notes
Platforms | Windows, macOS, Android, iOS | QA
Browsers | Chrome, Firefox, Edge, Safari (latest stable) | QA
Devices / views | Desktop, tablet, and mobile responsive views | QA
Network | Standard broadband and throttled mobile profile for UX checks | QA
Entry / Exit Criteria
Item | Details | Owner | Notes
Entry criteria | Environment available, test accounts ready, product catalog reachable, core flows not blocked, data prepared. | QA
Exit criteria | All critical scenarios executed, blocker/critical defects addressed or accepted, summary metrics updated. | QA
Deliverables
Item | Details | Owner | Notes
Outputs | Test plan, scenario catalogue, detailed test cases, RTM, defect log, execution report, and final test summary. | QA

## Scope & Risks
Scope, Assumptions, Risks & Mitigations
Scope Definition
Category | Area | Included? | Notes
Core flow | Search and browse | Yes | High-priority customer path
Core flow | Product detail page | Yes | Validate content, price, availability, CTA
Core flow | Cart and quantity updates | Yes | Totals and persistence matter
Core flow | Checkout and order placement | Yes | Business-critical
Account | Login / logout | Yes | Credential and error handling
Account | Order history | Yes | Post-purchase confidence
Non-functional | Responsive layout | Yes | Desktop, tablet, mobile
Non-functional | Accessibility baseline | Yes | Keyboard, labels, contrast
Integration | Warehouse backend | No | External to public web validation
Integration | Payment gateway internals | No | Only observable front-end behavior
Assumptions & Risks
Type | Description | Impact | Mitigation
Assumption | Stable public pages are available during testing | Medium | Use low-risk windows and record environment conditions
Assumption | Guest or test-safe checkout path is accessible | High | Use non-destructive validation points and screenshots
Risk | Frequent UI changes may invalidate locators or steps | High | Maintain locator strategy and prioritize stable checkpoints
Risk | Dynamic pricing / recommendations may change content | Medium | Validate behavior rather than exact merchandising results
Risk | Third-party dependencies may intermittently fail | Medium | Separate site defect vs external dependency issue
Risk | Production payment flow may restrict full-order execution | High | Use sandbox-safe checkpoints or order review boundary

## Scenarios
Scenario Catalogue
Scenario ID | Module | Scenario Name | Type | Priority | Automation? | Status | Business Value
TS-001 | Navigation | Open homepage and global menu | Smoke | High | Yes | Planned | High
TS-002 | Search | Search by keyword and review relevant results | Functional | High | Yes | Planned | High
TS-003 | Search | Apply filters and sorting on results | Functional | High | Yes | Planned | High
TS-004 | PDP | Validate product detail page content and CTA | Functional | High | Yes | Planned | High
TS-005 | Cart | Add item to cart from PDP | Smoke | Critical | Yes | Planned | High
TS-006 | Cart | Update item quantity and subtotal | Functional | High | Yes | Planned | High
TS-007 | Cart | Remove item from cart | Functional | High | Yes | Planned | Medium
TS-008 | Account | Login with valid credentials | Smoke | High | Yes | Planned | High
TS-009 | Account | Reject invalid credentials with clear error | Functional | High | Yes | Planned | Medium
TS-010 | Checkout | Proceed to checkout and validate shipping step | Smoke | Critical | Partial | Planned | High
TS-011 | Checkout | Validate payment selection and order review | Functional | Critical | Partial | Planned | High
TS-012 | Order | Verify order confirmation page | Functional | Critical | Partial | Planned | High
TS-013 | Order | Verify order history displays placed order | Functional | Medium | Yes | Planned | Medium
TS-014 | Responsive | Validate key flows on mobile viewport | Compatibility | High | No | Planned | High
TS-015 | Accessibility | Keyboard navigation and label checks | Accessibility | Medium | No | Planned | Medium

## Test Cases
Detailed Test Cases
TC ID | Scenario | Module | Title | Precondition | Test Steps | Expected Result | Type | Priority | Owner | Status
TC-001 | TS-002 | Search | Search by keyword | User is on homepage | 1. Enter 'laptop' in search bar 2. Submit search | Results page loads and shows relevant items for the query | Functional | High | QA | Not Run
TC-002 | TS-003 | Search | Apply category filter | Search results are displayed | 1. Select a category filter 2. Observe results | Result count and items update to reflect chosen filter | Functional | High | QA | Not Run
TC-003 | TS-003 | Search | Apply sort option | Search results are displayed | 1. Choose sort by Price: Low to High 2. Review first results | Displayed product order changes according to selected sort | Functional | Medium | QA | Not Run
TC-004 | TS-004 | PDP | Validate product details | A product listing is available | 1. Open a product 2. Review title, image, price, availability, shipping info | PDP shows complete, accurate, and readable product information | Functional | High | QA | Not Run
TC-005 | TS-005 | Cart | Add to cart from PDP | Product is purchasable | 1. Click Add to Cart 2. Open cart | Item is added, cart count updates, and product appears in cart | Smoke | Critical | QA | Not Run
TC-006 | TS-006 | Cart | Update quantity | Cart contains one item | 1. Change quantity from 1 to 2 | Quantity updates and subtotal recalculates correctly | Functional | High | QA | Not Run
TC-007 | TS-007 | Cart | Remove item from cart | Cart contains one item | 1. Remove cart item | Item is removed and subtotal updates accordingly | Functional | High | QA | Not Run
TC-008 | TS-008 | Account | Valid login | Known valid credentials are available | 1. Open sign-in page 2. Enter valid credentials 3. Submit | User is authenticated and routed to the signed-in experience | Smoke | High | QA | Not Run
TC-009 | TS-009 | Account | Invalid login | User is logged out | 1. Enter invalid password 2. Submit | Authentication is rejected and a clear error message is shown | Functional | High | QA | Not Run
TC-010 | TS-010 | Checkout | Proceed to checkout | Cart contains an available item | 1. Click Proceed to Checkout 2. Continue to shipping | Checkout starts successfully and required shipping fields are available | Smoke | Critical | QA | Not Run
TC-011 | TS-010 | Checkout | Validate required shipping fields | Checkout shipping step is open | 1. Leave mandatory fields empty 2. Try to continue | Required validation messages appear and continuation is blocked | Functional | High | QA | Not Run
TC-012 | TS-011 | Checkout | Select payment method | Shipping step completed | 1. Select a payment method 2. Continue to review | Selected payment option is retained on review step | Functional | Critical | QA | Not Run
TC-013 | TS-011 | Checkout | Review order total | Review step is visible | 1. Confirm item price, shipping, tax, total | Order summary displays consistent and correctly calculated totals | Functional | Critical | QA | Not Run
TC-014 | TS-012 | Order | Confirm order page | Order placement or review boundary is reached | 1. Complete final action or validate final checkpoint | Confirmation page or completion checkpoint is displayed with order reference | Functional | Critical | QA | Not Run
TC-015 | TS-013 | Order | Verify order history | Signed-in user has a recent order | 1. Open Orders page | Recent order appears with correct summary details | Functional | Medium | QA | Not Run
TC-016 | TS-014 | Responsive | Mobile viewport smoke | Mobile viewport is enabled | 1. Repeat homepage, search, PDP, cart smoke flow on mobile | Key actions remain usable and visually stable on mobile | Compatibility | High | QA | Not Run
TC-017 | TS-015 | Accessibility | Keyboard navigation | Keyboard-only navigation is used | 1. Tab through header, search, filters, cart, forms | Focus order is visible and interactive elements are reachable | Accessibility | Medium | QA | Not Run

## RTM
Requirements Traceability Matrix
Requirement ID | Requirement / Validation Area | Scenario ID | Test Case ID | Priority | Coverage Status
REQ-001 | Users can discover products using search | TS-002 | TC-001 | High | Covered
REQ-002 | Users can refine results using filters and sorting | TS-003 | TC-002 / TC-003 | High | Covered
REQ-003 | Users can review accurate product details before buying | TS-004 | TC-004 | High | Covered
REQ-004 | Users can add items to cart | TS-005 | TC-005 | Critical | Covered
REQ-005 | Users can update or remove cart items | TS-006 / TS-007 | TC-006 / TC-007 | High | Covered
REQ-006 | Users can sign in successfully | TS-008 | TC-008 | High | Covered
REQ-007 | Users receive proper feedback for invalid login | TS-009 | TC-009 | High | Covered
REQ-008 | Users can proceed through checkout shipping step | TS-010 | TC-010 / TC-011 | Critical | Covered
REQ-009 | Users can select payment and review totals | TS-011 | TC-012 / TC-013 | Critical | Covered
REQ-010 | Users can confirm and view placed order | TS-012 / TS-013 | TC-014 / TC-015 | Critical | Covered
REQ-011 | Core flow remains usable on mobile | TS-014 | TC-016 | High | Covered
REQ-012 | Baseline keyboard accessibility works | TS-015 | TC-017 | Medium | Covered

## Execution Tracker
Execution Tracker
TC ID | Scenario | Module | Cycle | Priority | Assigned To | Execution Date | Result | Comments
TC-001 | TS-002 | Search | Cycle 1 | High | QA |  | Pass | Relevant results displayed
TC-002 | TS-003 | Search | Cycle 1 | High | QA |  | Pass | Filter applied correctly
TC-003 | TS-003 | Search | Cycle 1 | Medium | QA |  | Blocked | Sort changed but price labels inconsistent
TC-004 | TS-004 | PDP | Cycle 1 | High | QA |  | Pass | PDP content displayed
TC-005 | TS-005 | Cart | Cycle 1 | Critical | QA |  | Pass | Item added successfully
TC-006 | TS-006 | Cart | Cycle 1 | High | QA |  | Fail | Subtotal did not update immediately
TC-007 | TS-007 | Cart | Cycle 1 | High | QA |  | Pass | Remove flow working
TC-008 | TS-008 | Account | Cycle 1 | High | QA |  | Pass | Valid login successful
TC-009 | TS-009 | Account | Cycle 1 | High | QA |  | Pass | Error message shown
TC-010 | TS-010 | Checkout | Cycle 1 | Critical | QA |  | Pass | Checkout reachable
TC-011 | TS-010 | Checkout | Cycle 1 | High | QA |  | Pass | Required shipping validation shown
TC-012 | TS-011 | Checkout | Cycle 1 | Critical | QA |  | Pass | Payment option retained
TC-013 | TS-011 | Checkout | Cycle 1 | Critical | QA |  | Fail | Order total mismatch vs line items
TC-014 | TS-012 | Order | Cycle 1 | Critical | QA |  | Blocked | Confirmation step unavailable due to environment constraint
TC-015 | TS-013 | Order | Cycle 1 | Medium | QA |  | Not Run | Dependent on order creation
TC-016 | TS-014 | Responsive | Cycle 1 | High | QA |  | Pass | Mobile smoke acceptable
TC-017 | TS-015 | Accessibility | Cycle 1 | Medium | QA |  | Pass | Keyboard focus visible

## Bug Tracker
Bug Tracker
Bug ID | Linked TC | Module | Summary | Severity | Priority | Status | Reported | Owner | Aging (Days) | Repro? | Notes
BUG-001 | TC-006 | Cart | Subtotal does not refresh immediately after quantity change | High | High | Open | 2026-04-14 | Dev | 0 | Yes | Observed after changing qty from 1 to 2
BUG-002 | TC-013 | Checkout | Order total mismatch between line items and final summary | Critical | Critical | Open | 2026-04-14 | Dev | 0 | Yes | Potential pricing/tax calculation issue
BUG-003 | TC-014 | Order | Confirmation page blocked by environment restriction | Medium | Medium | Blocked | 2026-04-14 | QA | 0 | Yes | Needs safe test path
Note on D3: Example defect seeded for portfolio presentation. Replace with real findings if you run live tests.

## Dashboard
QA Dashboard
Total Test Cases |  | Passed |  | Failed | Blocked
17 |  | 12 |  | 2 | 2
Not Run |  | Execution Progress |  | Open Bugs | Critical Bugs
1 |  | 94.12% |  | 2 | 1
Result | Count |  | Severity | Open Count
Pass | 12 |  | Critical | 1
Fail | 2 |  | High | 1
Blocked | 2 |  | Medium | 0
Not Run | 1 |  | Low | 0